## Comparison
Baseline
| FY 21 | FY 22 | FY 23 | FY 24 | FY 25 | FYDP
Projects | 20 | 28 | 17 | 17 | 24 | 106
Slack | 862 | 159 | 969 | 7175 | 1019 | 10184
Excursion A: Increase stability factor (1, 2, 4, 8, 16)
| FY 21 | FY 22 | FY 23 | FY 24 | FY 25 | FYDP
Projects | 21 | 27 | 14 | 16 | 14 | 92
Change | 1 | -1 | -3 | -1 | -10 | -14
Slack | 25 | 193 | 97455 | 52144 | 1444 | 151261
Change | -837 | 34 | 96486 | 44969 | 425 | 141077
Excursion B: Original stability factor; must fund P821 in FY23
| FY 21 | FY 22 | FY 23 | FY 24 | FY 25 | FYDP
Projects | 20 | 29 | 15 | 18 | 19 | 101
Change | 0 | 1 | -2 | 1 | -5 | -5
Slack | 3387 | 760 | 6963 | 4233 | 342 | 15685
Change | 2525 | 601 | 5994 | -2942 | -677 | 5501

## 20190219_MPAT_Solution_v3.2
Project Title | MIS Program | Location | Capability Sponsor | Must Fund | No Earlier | Stability | Current | Cost
SOF Command and Control Facility | SFCMD | FT BRAGG, NC | USASOC | FY 24 | FY 24 | FY 24 | FY 24 | 103000
SOF Operations Facility | CDA-J1 | CONUS CLASSIFIED | JSOC | FY 22 | FY 22 | FY 22 | FY 22 | 100000
SOF WARCOM Operations Support Facility | NSWCOM | Coronado, CA | NSW | ----- | FY 23 | FY 23 | FY 25 | 77000
SOF NSWG2 NSWTG Combat Service Support Facilities | NSWG2 | JOINT EXPEDITIONARY BASE LITTLE CREEK - STORY | NSW | FY 21 | FY 21 | FY 21 | FY 21 | 58000
SOF Joint Intelligence Center | SFCMD | FT BRAGG, NC | USASOC | FY 22 | FY 22 | FY 22 | FY 22 | 56100
SOF Dry Combat Submersible Operations Facility and Command Center | NSWG3 | JOINT EXPEDITIONARY BASE LITTLE CREEK - STORY | NSW | ----- | FY 21 | FY 21 | FY 21 | 54500
SOF SOUC Training Facility | NSWCEN | Fort Pickett, VA | NSW | ----- | FY 21 | FY 21 | FY 21 | 50000
SOF Hangar | 160SOR | YUMA, AZ | USASOC | FY 21 | FY 21 | FY 21 | FY 21 | 48732
SOF Group Headquarters | 3SFG | FT BRAGG, NC | USASOC | FY 21 | FY 21 | FY 21 | FY 21 | 48000
SOF Special Tactics Operations Facility (23 STS) | 24SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 21 | FY 21 | FY 21 | 44810
SOF Military Free Fall Advanced Training Complex | SWCS | YUMA, AZ | USASOC | ----- | FY 21 | FY 21 | FY 21 | 44800
SOF Battalion Operations Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 23 | 41000
SOF Operations Faciltiy | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 22 | FY 22 | FY 22 | 40000
SOF Group HQs Expansion | 10SFG | FT CARSON, CO | USASOC | ----- | FY 22 | FY 22 | FY 22 | 40000
SOF Combat Aircraft Parking Apron-North | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 21 | FY 21 | FY 21 | 38310
SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | FY 22 | FY 22 | FY 22 | 35000
SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | FY 21 | FY 21 | FY 21 | 35000
SOF Multi-Purpose Range | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | FY 23 | FY 23 | 32000
SOF SEAL Team SEVENTEEN Operations Facility | NSWG11 | Coronado, CA | NSW | ----- | FY 22 | FY 24 | FY 24 | 30600
SOF Small Arms Range | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 22 | FY 22 | FY 22 | 30400
SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | FY 23 | FY 24 | FY 25 | 27000
SOF SERE Training Facility | NSWCEN | Coronado, CA | NSW | ----- | FY 21 | FY 21 | FY 21 | 26500
SOF Hangar | 160SOR | NELLIS AFB, NV | USASOC | ----- | FY 23 | FY 24 | FY 25 | 26000
SOF TRADET TWO Operations Facility | NSWG2 | Little Creek, VA | NSW | ----- | FY 23 | FY 23 | FY 23 | 25900
SOF Indoor Dynamic Shooting Facility | NSWG3 | Pearl City, HI | NSW | ----- | FY 22 | FY 22 | FY 22 | 24845
SOF Operations and Maintenance Facilities | SOAWC | DUKE FIELD, FL EGLIN AFB, FL AUX FIELD (DUKE) | AFSOC | FY 22 | FY 22 | FY 22 | FY 22 | 23600
SOF Human Performance Training Center | NSWG2 | Little Creek, VA | NSW | FY 21 | FY 21 | FY 21 | FY 21 | 23200
SOCCENT Operations Facility | SOCCENT | MacDill AFB, FL | SOCCENT | ----- | FY 24 | FY 24 | FY 24 | 21181
SOF MI Battalion Operations Facility | SUSB | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 24 | FY 24 | 21000
SOF Dry Deck Shelter Operations Facility | NSWG3 | Little Creek, VA | NSW | ----- | FY 22 | ----- | FY 25 | 20685
SOF SBT20 Combatant Craft Operations Facility | NSWG4 | Little Creek, VA | NSW | ----- | FY 22 | FY 24 | FY 24 | 20685
SOF Operations Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 20543
SOF Integrated Operations Facility | SOAWC | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | FY 23 | FY 23 | 20500
SOF Cold Water Training Austere Environment Facility | NSWG3 | Keyport, WA | NSW | ----- | FY 21 | ----- | FY 25 | 20500
SOF ATC Operations Support Facility | NSWCEN | Coronado, CA | NSW | ----- | FY 21 | FY 21 | FY 21 | 20200
SOF Tactical Equipment Maintenance Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | FY 22 | FY 22 | FY 23 | 20000
SOF MI Battalion Headquarters | 75RGR | FT BENNING, GA | USASOC | FY 22 | FY 22 | FY 22 | FY 22 | 20000
SOF Indoor Range | 75RGR | HUNTER AAF, GA | USASOC | ----- | FY 22 | FY 22 | FY 22 | 19500
SOF Ready Building | SWCS | YUMA, AZ | USASOC | FY 21 | FY 21 | FY 21 | FY 21 | 19051
SOF Human Performance Training Center | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 18500
SOF UAV Avionics Maintenance and Storage Facility | NSWG10 | Coronado, CA | NSW | ----- | FY 22 | FY 22 | FY 22 | 17400
SOF Readiness Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | FY 23 | FY 24 | FY 24 | 17000
SOF NSWU-3 Operations Support Facility | NSWG1 | Bahrain | NSW | ----- | FY 22 | ----- | FY 25 | 16800
SOF Tactical Equipment Maintenance Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 21 | FY 21 | FY 21 | 16500
SOF Fuel Cell Hangar | SOAWC | EGLIN AFB, FL AUX FIELD (DUKE) | AFSOC | ----- | FY 22 | FY 23 | FY 23 | 16200
SOF Marine Raider Support Battalion and Unmanned Aerial System Facilities | MSOSG | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | FY 25 | 16000
SOF Human Performance Training Center | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 23 | FY 23 | FY 23 | FY 23 | 15000
SOF Combat Service Support/Motor Transport Maintenance Expansion | MSOSG | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | FY 25 | 15000
SOF Combatant Craft Launch and Recovery Facility | NSWG4 | San Clemente Island, CA | NSW | ----- | FY 23 | ----- | FY 25 | 14800
SOF Mission Rehearsal Landing Zone | 27SOW | CANNON AFB, NM | AFSOC | ----- | FY 23 | ----- | FY 25 | 14700
SOF Training Facility | SOCEUR | Riga, Latvia | SOCEUR | FY 22 | FY 22 | ----- | FY 22 | 14700
SOF Operations Building Addition | CDA-N | DAM NECK, VA | JSOC | FY 21 | FY 21 | FY 21 | FY 21 | 14400
SOF Support Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 13603
SOF Tactical Equipment Maintenance Facility | 10SFG | FT CARSON, CO | USASOC | ----- | FY 21 | FY 21 | FY 21 | 13600
SOF SERE Training Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | FY 24 | FY 24 | 13300
SOF Simulator Facility (AC-130J) | SOAWC | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | ----- | FY 25 | 13000
SOF EOD Facility | MSOR | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | FY 25 | 13000
SOF Operations Facility | SOCEUR | Lubliniec, Poland | SOCEUR | FY 25 | FY 23 | ----- | FY 25 | 13000
SOF Human Performance Training Center | 353SOG | KADENA AB, JP | AFSOC | FY 22 | FY 22 | FY 22 | FY 22 | 12960
SOF Combat Swimmer Training Facility | NSWG2 | Key West, FL | NSW | ----- | FY 23 | FY 24 | FY 24 | 12960
SOF Operations Building | CDA-F3 | FT BRAGG, NC | JSOC | FY 22 | FY 22 | FY 22 | FY 22 | 12800
SOF Deployment Readiness Warehouse | 7SFG | Eglin AFB, FL | USASOC | ----- | FY 23 | FY 23 | FY 23 | 12800
SOF Military Working Dog Facility | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 21 | FY 21 | FY 21 | 12700
SOF Operations Facility | SOCEUR | Kaunas, Lithuania | SOCEUR | FY 25 | FY 22 | ----- | FY 25 | 12600
SOF Vehicle Maintenance Facility | SWCS | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 23 | 12376
SOF Training Facility Addition | CDA-N | Dam Neck, VA | JSOC | ----- | FY 23 | FY 23 | FY 23 | 12300
SOF Training Tank Expansion | MSOR | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | FY 22 | FY 22 | 12100
SOF Training Aid and Mock-Up Storage Facility | CDA-N | Dam Neck, VA | JSOC | ----- | FY 22 | FY 22 | FY 22 | 12000
SOF Support Facility Expansions | MSOR | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | FY 25 | 12000
SOF SOAT-B HQ | 160SOT | FT CAMPBELL, KY | USASOC | ----- | FY 24 | ----- | FY 25 | 12000
SOF Company Operations Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | FY 25 | 11800
SOF Readiness Facility | 160SOR | HUNTER AAF, GA | USASOC | ----- | FY 24 | ----- | FY 25 | 11800
SOF Technical Support Detachment (TSD) Annex | 3SFG | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 23 | 11800
SOF Close Quarters Combat Facility | NSWG3 | Pearl City, HI | NSW | ----- | FY 22 | ----- | FY 25 | 11600
SOF Language Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 11600
SOF Operations Facility | SOCEUR | Riga, Latvia | SOCEUR | FY 24 | FY 22 | ----- | FY 24 | 11350
SOF FOB Freedom Upgrades | SWCS | FT BRAGG, NC | USASOC | ----- | FY 22 | ----- | FY 25 | 11000
SOF Battalion Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 10888
SOF Human Performance Training Center | 75RGR | FT BENNING, GA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 10645
SOF Vehicle Shelter | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 24 | FY 24 | FY 24 | 10400
SOF HPTC Facility | CDA-F3 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | FY 25 | 10000
SOF CONTROLLED HUMIDITY WAREHOUSE | SOCSOUTH | HOMESTEAD, FL | SOCSOUTH | ----- | FY 23 | FY 23 | FY 23 | 9604
Training Target Structure | CDA-J1 | CONUS CLASSIFIED | JSOC | ----- | FY 21 | FY 21 | FY 21 | 9200
SOF Deployment Facility | CDA-A1 | FT Bragg, NC | JSOC | ----- | FY 22 | FY 23 | FY 23 | 9000
SOF Human Performance Training Center | 24SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 21 | FY 22 | FY 22 | 8915
SOF Simulator Facility EC-130J | 193SOW | HARRISBURG ANG, PA | AFSOC | ----- | FY 22 | FY 23 | FY 23 | 8900
SOF Simulator Facility (Manned ISR) | SOAWC | HURLBURT FIELD, FL | AFSOC | ----- | FY 25 | FY 25 | FY 25 | 8500
SOF NSWG11 Operations Support Facility | NSWG11 | Coronado, CA | NSW | ----- | FY 22 | FY 22 | FY 22 | 7600
SOF Operations Facility Renovation | CDA-N | DAM NECK, VA | JSOC | FY 21 | FY 21 | FY 21 | FY 21 | 7500
SOF Multi-Purpose Range Support Facility | SWCS | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 25 | 7500
SOF Research Analytic Center | 4MISG | FT BRAGG, NC | USASOC | ----- | FY 24 | ----- | FY 25 | 7500
SOF Military Working Dog Facility | 75RGR | HUNTER AAF, GA | USASOC | ----- | FY 22 | FY 22 | FY 22 | 7400
SOF Multi Purpose Canine Facility | NSWG1 | Coronado, CA | NSW | ----- | FY 21 | FY 22 | FY 22 | 7230
SOF Close Quarters Combat Range | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 21 | FY 21 | FY 22 | 7200
SOF Baffle Containment for Range 19C | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 22 | FY 22 | FY 22 | 7100
SOF Supply Support Activity | 3SFG | FT BRAGG, NC | USASOC | ----- | FY 22 | FY 22 | FY 22 | 6400
SOF Paraloft Expansion | MSOR | CAMP LEJEUNE, NC | MARSOC | FY 21 | FY 21 | FY 21 | FY 21 | 6228
SOF Operations Facility | 5SFG | FT CAMPBELL, KY | USASOC | ----- | FY 23 | FY 23 | FY 23 | 4700
SOF Training Facility | SOCEUR | Kaunas, Lithuania | SOCEUR | FY 23 | FY 22 | ----- | FY 23 | 4600
SOF Arms Room Addition | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 22 | FY 22 | FY 22 | 4500
SOF NSWG-4 Finger Piers | NSWG4 | Little Creek, VA | NSW | ----- | FY 23 | FY 24 | FY 24 | 4500
SOF Mackall Company Operations Facilities | SWCS | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 24 | FY 24 | 4350
SOF RSTA Operations Facility | 75RGR | FT BENNING, GA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 4150
SOF Communications Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 4109
SOF RIGGING AND DRYING FACILITY | SOCSOUTH | HOMESTEAD, FL | SOCSOUTH | ----- | FY 23 | FY 23 | FY 23 | 3960
SOF Tactical Unmanned Aerial Vehicle Hangar | 1SFG | FT LEWIS, WA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 3800
SOF Add Alter Simulator Facility (Manned ISR) | SOAWC | CANNON AFB, NM | AFSOC | ----- | ----- | FY 27 | ----- | 0
SOF Parking Apron (AC-130J) | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 22 | ----- | ----- | 0
SOF AMU/Hangar (AC-130J) | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | ----- | ----- | 0
SOF Hangar/AMU (CV-22) | 27SOW | CANNON AFB, NM | AFSOC | ----- | FY 23 | ----- | ----- | 0
SOF Hangar/AMU (MC-130J) | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | ----- | ----- | 0
SOF 22 STS Operational Training Facilities | 24SOW | JOINT BASE LEWIS MCCHORD, WA | AFSOC | ----- | ----- | ----- | ----- | 0
SOF Mobility Aerial Delivery Facility | 27SOW | CANNON AFB, NM | AFSOC | ----- | ----- | ----- | ----- | 0
SOF JMWC Facility | HQSOCOM | MacDill AFB, FL | HQSOCOM | ----- | FY 22 | ----- | ----- | 0
SOF Equipment Development Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
SOF Multi-Purpose Ops Facility | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | ----- | ----- | 0
SOF Operational Ammunition Supply Point | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
SOF Mission Command Center | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 22 | ----- | ----- | 0
SOF Deployment and Distribution Center Addition | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
SOF Logistics Support Facility | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | ----- | ----- | 0
SOF Tactical Ground Mobility Ops and Storage Facility | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | ----- | ----- | 0
Joint Communicaitons Training Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 25 | ----- | ----- | 0
SOF Training Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 25 | ----- | ----- | 0
SOF Ops Facility | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 25 | ----- | ----- | 0
SOF NSWG-4 Operations Support Facility | NSWG4 | Little Creek, VA | NSW | ----- | FY 22 | ----- | ----- | 0
SOF Land Warfare Training Ranges | NSWCEN | Niland, CA | NSW | ----- | FY 22 | ----- | ----- | 0
SOF SEAL Team EIGHTEEN Ops Facility | NSWG11 | Little Creek, VA | NSW | ----- | FY 24 | ----- | ----- | 0
SOF SRT-2 Operations Facility | NSWG10 | Little Creek, VA | NSW | ----- | FY 23 | ----- | ----- | 0
SOF Breacher Training Facility | NSWCEN | Fort Pickett, VA | NSW | ----- | FY 23 | ----- | ----- | 0
SOF Small Craft Operations Facility | NSWCEN | Kodiak, AK | NSW | ----- | FY 23 | ----- | ----- | 0
SOF NSWU-3 Operations Support Facility #2 | NSWG1 | Bahrain | NSW | ----- | ----- | ----- | ----- | 0
SOF NSWU-1 Air Operations Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
SOF NSWU-1 Dive Operations Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
SOF NSWU-1 Training Support Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
SOF NAVSCIATTS Training Support Facilities | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
SOF NAVSCIATTS Operations Support Facility | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
SOF NAVSCIATTS Partner Nation Student Quarters | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
SOF Human Performance Training Center | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
SOF SBT-22 Operations Facilities | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
SOF SBT-22 Boat Support Facilities | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
SOF NAVSCIATTS Boat Ramp/Small Craft Berthing | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
SOF NSWU-1 Operations Support Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
SOCFWD-EA OPERATIONS FACILITY | SOCAFRICA | CAMP LEMONNIER, DJIBOUTI | SOCAF | ----- | ----- | ----- | ----- | 0
TSOC HQ, SOCAFRICA | SOCAFRICA | KELLEY BARRACKS, STUTTGART, GERMANY | SOCAF | ----- | ----- | ----- | ----- | 0
TSOC HQ, SOCEUR | SOCEUR | Patch Barracks, Stuttgart, Germany | SOCEUR | ----- | ----- | ----- | ----- | 0
SOF Consolidated Rigging Facility | 1SFG | JOINT BASE LEWIS-MCCHORD, WA | USASOC | ----- | FY 21 | FY 21 | ----- | 0
SOF USASOC Headquarters Complex | USASOC | FT BRAGG, NC | USASOC | ----- | FY 22 | FY 22 | ----- | 0
SOF Battalion Operations Facility | 1SFG | JOINT BASE LEWIS-MCCHORD, WA | USASOC | ----- | FY 23 | FY 24 | ----- | 0
SOF Group Headquarters | 1SFG | JOINT BASE LEWIS-MCCHORD, WA | USASOC | ----- | FY 24 | ----- | ----- | 0
SOF Media Operations Center Modernization and Expansion | 4MISG | FT BRAGG, NC | USASOC | ----- | FY 24 | ----- | ----- | 0
SOF Hangar | 160SOT | FT CAMPBELL, KY | USASOC | ----- | FY 24 | ----- | ----- | 0
SOF Hangar and Aviation COF | 160SOR | HUNTER AAF, GA | USASOC | ----- | FY 24 | ----- | ----- | 0
SOF Forward Support Company COFs | 3SFG | FT. BRAGG, NC | USASOC | ----- | FY 24 | ----- | ----- | 0
SOF Battalion HQ/CO Operations Addition | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 24 | ----- | ----- | 0
SOF Hangar and Aviation COF | 160SOR | HUNTER AAF, GA | USASOC | ----- | FY 24 | ----- | ----- | 0
SOF Regiment HQ Support Annex | 75RGR | FT BENNING, GA | USASOC | ----- | FY 24 | ----- | ----- | 0
SOF Battalion Tactical Equipment Maintenance Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Deployment Readiness Warehouse | 95CABDE | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Command Headquarters | SFCMD | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Tactical Equipment Maintenance Facility | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Admin/Company Operations | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Regiment and Battalion HQs | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Deployment Equipment Storage Building | 75RGR | FT BENNING, GA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Human Performance Training Center | 5SFG | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Expand Battalion Headquarters Building | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Deployment Storage Facility (BN Deployment) | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SOF Company Operations Facility (CRF Co) | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SOF Hangar and Aviation Company Operations Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Readiness Facility | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SOF BLDGS 7402 and 7404 Modernization | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
Language Regional Expertise and Cultural Center | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF D3915 Renovation Bank Hall | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Battalion Headquarters | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Language Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Consolidated COF | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
PSYOP Battalion Operations Facility Renovation (H3014) | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Battalion Operations Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Watercraft Storage Facility | SWCS | NAS KEY WEST, FL | USASOC | ----- | ----- | ----- | ----- | 0
SOF 4th MISG Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Hangar Addition | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Unit Storage / Mobilization Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
4x HSC Company Operations Facility Renovation (H2908, H2919) | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF TAPO Facility | 160SOR | Joint Base Langley Eustis, VA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Human Performance Training Center | 7SFG | Eglin AFB, FL | USASOC | ----- | ----- | ----- | ----- | 0
SOF Logistics Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
1x Three Company Operations Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Deployment Readiness Warehouse | 160SOR | HUNTER AAF, GA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Advanced Techniques Facility | SWCS | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Advanced Skills Company Facility | 5SFG | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF MISG HQ Renovation | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Sniper Rappel Tower | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SOF Deployment Readiness Warehouse | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Surgical Strike Training Complex, Phase I | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
Son Tay Utilities and AT/FP Upgrade | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Deployment Readiness Warehouse | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Surgical Strike Training Complex, Phase II | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Maritime Ops Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Battalion Operations Facility | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
SOF Deployment Readiness Warehouse | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Human Performance Training Center | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
Cultural Language Facility | 95CABDE | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Tactical Equipment Maintenance Facility | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Combat Divers Training Support Facility | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
SOF Deployment Readiness Warehouse | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
Operational Skills Detachment | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
Skills Enhancement and Support Building | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Sensitive Activities Training Facility | 1SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
Renovate H2309 (Legal, SHARP, FSRA, EO/EEO) | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
Assessment and Selection Complex Alpha | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
SOF Tactical Equipment Maintenance Facility | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Tactical Equipment Maintenance Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Human Performance Training Facility | 75RGR | HUNTER AAF, GA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Tactical Equipment Maintenance Facility | SUSB | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Consolidated Rigging Facility | 75RGR | HUNTER AAF, GA | USASOC | ----- | ----- | ----- | ----- | 0
1x PSYOP Battalion Operations Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
Assessment and Selection Complex Charlie | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
SOF Surgical Strike Training Complex PH3 | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Training and Operations Facility | USASOC | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Language Facility | 7SFG | Eglin AFB, FL | USASOC | ----- | ----- | ----- | ----- | 0
1x PSYOP Battalion Operations Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
Assessment and Selection Complex Bravo | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
SOF Heavy Drop Rigging Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Human Performance Training Center | 75RGR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SOF Combat Water Survival Training Facility | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
Extend Psyops Lane through Hotel Campus | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Storage Warehouse | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Combat Water Survival Training Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Access Control Point | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Combat Diving Training Tank | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
SOF Combat Water Survival Training Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
Re-establish Son Tay Road and Resurface Sapper Street | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Combat Water Survival Training Facility | 5SFG | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Human Performance Training Center | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Combat Water Survival Training Facility | 7SFG | Eglin AFB, FL | USASOC | ----- | ----- | ----- | ----- | 0
SOF Parking Deck | USASOC | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Surgical Strike Training Complex PH4 | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Hangar | 160SOT | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Surgical Strike Training Complex, PH 5 | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Consolidated Divers Tng Facilty | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
Renovate KW100 | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
Parking Deck Garage | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SOF Parking Deck Bryant Hall | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Airborne Staging Facility, MAAF | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SOF Rigger Facility Annex | SUSB | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0

## 20190221_MPAT_Solution_v3.2 a
Project Number | Project Title | MIS Program | Location | Capability Sponsor | Must Fund | No Earlier | Stability | Current | Cost
FTEV153011 | SOF Combat Aircraft Parking Apron-North | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 21 | FY 21 | FY 21 | 38310
FTEV103005 | SOF Special Tactics Operations Facility (23 STS) | 24SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 21 | FY 21 | FY 21 | 44810
LXEZ163901 | SOF Human Performance Training Center | 353SOG | KADENA AB, JP | AFSOC | FY 22 | FY 22 | FY 22 | FY 22 | 12960
92242 | SOF Battalion Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 10888
92243 | SOF Operations Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 20543
92351 | SOF Communications Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 4109
92352 | SOF Support Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 13603
72426 | SOF Military Working Dog Facility | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 21 | FY 21 | FY 21 | 12700
81890 | Training Target Structure | CDA-J1 | CONUS CLASSIFIED | JSOC | ----- | FY 21 | FY 21 | FY 21 | 9200
P1075 | SOF Operations Building Addition | CDA-N | DAM NECK, VA | JSOC | FY 21 | FY 21 | FY 21 | FY 21 | 14400
P1068 | SOF Operations Facility Renovation | CDA-N | DAM NECK, VA | JSOC | FY 21 | FY 21 | FY 21 | FY 21 | 7500
69253 | SOF Close Quarters Combat Range | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 21 | FY 21 | FY 21 | 7200
P1411 | SOF Paraloft Expansion | MSOR | CAMP LEJEUNE, NC | MARSOC | FY 21 | FY 21 | FY 21 | FY 21 | 6228
P907 | SOF Dry Combat Submersible Operations Facility and Command Center | NSWG3 | JOINT EXPEDITIONARY BASE LITTLE CREEK - STORY | NSW | ----- | FY 21 | FY 21 | FY 21 | 54500
P997 | SOF NSWG2 NSWTG Combat Service Support Facilities | NSWG2 | JOINT EXPEDITIONARY BASE LITTLE CREEK - STORY | NSW | FY 21 | FY 21 | FY 21 | FY 21 | 58000
P911 | SOF SERE Training Facility | NSWCEN | Coronado, CA | NSW | ----- | FY 21 | FY 21 | FY 21 | 26500
P951 | SOF ATC Operations Support Facility | NSWCEN | Coronado, CA | NSW | ----- | FY 21 | FY 21 | FY 21 | 20200
P177 | SOF SOUC Training Facility | NSWCEN | Fort Pickett, VA | NSW | ----- | FY 21 | FY 21 | FY 21 | 50000
87437 | SOF Group Headquarters | 3SFG | FT BRAGG, NC | USASOC | FY 21 | FY 21 | FY 21 | FY 21 | 48000
81907 | SOF Consolidated Rigging Facility | 1SFG | JOINT BASE LEWIS-MCCHORD, WA | USASOC | ----- | FY 21 | FY 21 | ----- | 0
66326 | SOF Tactical Equipment Maintenance Facility | 10SFG | FT CARSON, CO | USASOC | ----- | FY 21 | FY 21 | FY 21 | 13600
86022 | SOF Hangar | 160SOR | YUMA, AZ | USASOC | FY 21 | FY 21 | FY 21 | FY 21 | 48732
85959 | SOF Ready Building | SWCS | YUMA, AZ | USASOC | FY 21 | FY 21 | FY 21 | FY 21 | 19051
81906 | SOF Military Free Fall Advanced Training Complex | SWCS | YUMA, AZ | USASOC | ----- | FY 21 | FY 21 | FY 21 | 44800
91018 | SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | FY 21 | FY 21 | FY 21 | 35000
89186 | SOF Tactical Equipment Maintenance Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 21 | FY 21 | FY 21 | 16500
FTEV123008 | SOF Human Performance Training Center | 24SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 21 | FY 22 | FY 22 | 8915
AFSOC180001 | SOF Operations and Maintenance Facilities | SOAWC | DUKE FIELD, FL EGLIN AFB, FL AUX FIELD (DUKE) | AFSOC | FY 22 | FY 22 | FY 22 | FY 22 | 23600
FTEV123003 | SOF Small Arms Range | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 22 | FY 22 | FY 22 | 30400
88658 | SOF Operations Faciltiy | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 22 | FY 22 | FY 22 | 40000
92746 | SOF Operations Facility | CDA-J1 | CONUS CLASSIFIED | JSOC | FY 22 | FY 22 | FY 22 | FY 22 | 100000
90610 | SOF Arms Room Addition | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 22 | FY 22 | FY 22 | 4500
92793 | SOF Operations Building | CDA-F3 | FT BRAGG, NC | JSOC | FY 22 | FY 22 | FY 22 | FY 22 | 12800
P672 | SOF Training Aid and Mock-Up Storage Facility | CDA-N | Dam Neck, VA | JSOC | ----- | FY 22 | FY 22 | FY 22 | 12000
69252 | SOF Baffle Containment for Range 19C | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 22 | FY 22 | FY 23 | 7100
P1284 | SOF Training Tank Expansion | MSOR | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | FY 22 | FY 22 | 12100
P967 | SOF Multi Purpose Canine Facility | NSWG1 | Coronado, CA | NSW | ----- | FY 21 | FY 22 | FY 22 | 7230
P912 | SOF NSWG11 Operations Support Facility | NSWG11 | Coronado, CA | NSW | ----- | FY 22 | FY 22 | FY 22 | 7600
P477 | SOF Indoor Dynamic Shooting Facility | NSWG3 | Pearl City, HI | NSW | ----- | FY 22 | FY 22 | FY 22 | 24845
P870 | SOF UAV Avionics Maintenance and Storage Facility | NSWG10 | Coronado, CA | NSW | ----- | FY 22 | FY 22 | FY 22 | 17400
92792 | SOF MI Battalion Headquarters | 75RGR | FT BENNING, GA | USASOC | FY 22 | FY 22 | FY 22 | FY 22 | 20000
71229 | SOF Tactical Equipment Maintenance Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | FY 22 | FY 22 | FY 22 | 20000
81896 | SOF Indoor Range | 75RGR | HUNTER AAF, GA | USASOC | ----- | FY 22 | FY 22 | FY 22 | 19500
69518 | SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | FY 22 | FY 22 | FY 22 | 35000
69262 | SOF Military Working Dog Facility | 75RGR | HUNTER AAF, GA | USASOC | ----- | FY 22 | FY 22 | FY 22 | 7400
79460 | SOF Group HQs Expansion | 10SFG | FT CARSON, CO | USASOC | ----- | FY 22 | FY 22 | FY 22 | 40000
87447 | SOF Supply Support Activity | 3SFG | FT BRAGG, NC | USASOC | ----- | FY 22 | FY 22 | FY 22 | 6400
92791 | SOF Joint Intelligence Center | SFCMD | FT BRAGG, NC | USASOC | FY 22 | FY 22 | FY 22 | FY 22 | 56100
91019 | SOF USASOC Headquarters Complex | USASOC | FT BRAGG, NC | USASOC | ----- | FY 22 | FY 22 | ----- | 0
FTFA173001 | SOF Fuel Cell Hangar | SOAWC | EGLIN AFB, FL AUX FIELD (DUKE) | AFSOC | ----- | FY 22 | FY 23 | FY 23 | 16200
SHYQ149104 | SOF Simulator Facility EC-130J | 193SOW | HARRISBURG ANG, PA | AFSOC | ----- | FY 22 | FY 23 | FY 23 | 8900
FTEV163002 | SOF Integrated Operations Facility | SOAWC | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | FY 23 | FY 25 | 20500
FTEV073023 | SOF Vehicle Shelter | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 24 | FY 24 | FY 24 | 10400
P155 | SOF Training Facility Addition | CDA-N | Dam Neck, VA | JSOC | ----- | FY 23 | FY 23 | FY 23 | 12300
P619 | SOF Multi-Purpose Range | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | FY 23 | FY 25 | 32000
81893 | SOF Deployment Facility | CDA-A1 | FT Bragg, NC | JSOC | ----- | FY 22 | FY 23 | FY 23 | 9000
P821 | SOF WARCOM Operations Support Facility | NSWCOM | Coronado, CA | NSW | ----- | FY 23 | FY 23 | FY 25 | 77000
P901 | SOF TRADET TWO Operations Facility | NSWG2 | Little Creek, VA | NSW | ----- | FY 23 | FY 23 | FY 23 | 25900
KYJM87817 | SOF CONTROLLED HUMIDITY WAREHOUSE | SOCSOUTH | HOMESTEAD, FL | SOCSOUTH | ----- | FY 23 | FY 23 | FY 23 | 9604
KYJM87846 | SOF RIGGING AND DRYING FACILITY | SOCSOUTH | HOMESTEAD, FL | SOCSOUTH | ----- | FY 23 | FY 23 | FY 23 | 3960
80777 | SOF Battalion Operations Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 25 | 41000
87441 | SOF Operations Facility | 5SFG | FT CAMPBELL, KY | USASOC | ----- | FY 23 | FY 23 | FY 25 | 4700
91021 | SOF Deployment Readiness Warehouse | 7SFG | Eglin AFB, FL | USASOC | ----- | FY 23 | FY 23 | FY 23 | 12800
91022 | SOF Technical Support Detachment (TSD) Annex | 3SFG | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 23 | 11800
63848 | SOF Vehicle Maintenance Facility | SWCS | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 23 | 12376
89187 | SOF Multi-Purpose Range Support Facility | SWCS | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 23 | 7500
FTEV173002 | SOF Simulator Facility (Manned ISR) | SOAWC | HURLBURT FIELD, FL | AFSOC | ----- | FY 25 | FY 25 | FY 25 | 8500
CZQZ093010 | SOF Add Alter Simulator Facility (Manned ISR) | SOAWC | CANNON AFB, NM | AFSOC | ----- | ----- | FY 27 | ----- | 0
88654 | SOF SERE Training Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | FY 24 | FY 24 | 13300
P904 | SOF SEAL Team SEVENTEEN Operations Facility | NSWG11 | Coronado, CA | NSW | ----- | FY 22 | FY 24 | FY 25 | 30600
P654 | SOF SBT20 Combatant Craft Operations Facility | NSWG4 | Little Creek, VA | NSW | ----- | FY 22 | FY 24 | FY 24 | 20685
P902 | SOF Combat Swimmer Training Facility | NSWG2 | Key West, FL | NSW | ----- | FY 23 | FY 24 | FY 24 | 12960
P568 | SOF NSWG-4 Finger Piers | NSWG4 | Little Creek, VA | NSW | ----- | FY 23 | FY 24 | FY 24 | 4500
NVZR173711 | SOCCENT Operations Facility | SOCCENT | MacDill AFB, FL | SOCCENT | ----- | FY 24 | FY 24 | FY 24 | 21181
87436 | SOF Battalion Operations Facility | 1SFG | JOINT BASE LEWIS-MCCHORD, WA | USASOC | ----- | FY 23 | FY 24 | FY 25 | 93000
91020 | SOF Language Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 11600
93282 | SOF Hangar | 160SOR | NELLIS AFB, NV | USASOC | ----- | FY 23 | FY 24 | FY 25 | 26000
89192 | SOF MI Battalion Operations Facility | SUSB | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 24 | FY 24 | 21000
93283 | SOF Readiness Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | FY 23 | FY 24 | FY 24 | 17000
81170 | SOF Human Performance Training Center | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 18500
69279 | SOF Tactical Unmanned Aerial Vehicle Hangar | 1SFG | FT LEWIS, WA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 3800
89193 | SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | FY 23 | FY 24 | FY 25 | 27000
81901 | SOF RSTA Operations Facility | 75RGR | FT BENNING, GA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 4150
86027 | SOF Mackall Company Operations Facilities | SWCS | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 24 | FY 24 | 4350
92790 | SOF Command and Control Facility | SFCMD | FT BRAGG, NC | USASOC | FY 24 | FY 24 | FY 24 | FY 24 | 103000
79445 | SOF Human Performance Training Center | 75RGR | FT BENNING, GA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 10645
FTEV153012 | SOF Parking Apron (AC-130J) | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 22 | ----- | ----- | 0
1055863 | SOF AMU/Hangar (AC-130J) | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | ----- | ----- | 0
CZQZ183001 | SOF Hangar/AMU (CV-22) | 27SOW | CANNON AFB, NM | AFSOC | ----- | FY 23 | ----- | ----- | 0
PXLY073001 | SOF Mission Rehearsal Landing Zone | 27SOW | CANNON AFB, NM | AFSOC | ----- | FY 23 | ----- | ----- | 0
1073614 | SOF Simulator Facility (AC-130J) | SOAWC | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | ----- | ----- | 0
1055876 | SOF Hangar/AMU (MC-130J) | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | ----- | ----- | 0
PQWY183001 | SOF 22 STS Operational Training Facilities | 24SOW | JOINT BASE LEWIS MCCHORD, WA | AFSOC | ----- | ----- | ----- | ----- | 0
CZQZ073019 | SOF Mobility Aerial Delivery Facility | 27SOW | CANNON AFB, NM | AFSOC | ----- | ----- | ----- | ----- | 0
92241 | SOF Human Performance Training Center | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 23 | FY 23 | FY 23 | FY 23 | 15000
TBD1 | SOF JMWC Facility | HQSOCOM | MacDill AFB, FL | HQSOCOM | ----- | FY 22 | ----- | ----- | 0
88656 | SOF Equipment Development Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
P1052 | SOF Multi-Purpose Ops Facility | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | ----- | ----- | 0
94023 | SOF Operational Ammunition Supply Point | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
92107 | SOF Mission Command Center | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 22 | ----- | ----- | 0
90510 | SOF Deployment and Distribution Center Addition | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
94051 | SOF HPTC Facility | CDA-F3 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
P167 | SOF Logistics Support Facility | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | ----- | ----- | 0
87741 | SOF Company Operations Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
P163 | SOF Tactical Ground Mobility Ops and Storage Facility | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | ----- | ----- | 0
TBD2 | Joint Communicaitons Training Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 25 | ----- | ----- | 0
88655 | SOF Training Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 25 | ----- | ----- | 0
92397 | SOF Ops Facility | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 25 | ----- | ----- | 0
P1537 | SOF Marine Raider Support Battalion and Unmanned Aerial System Facilities | MSOSG | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | ----- | 0
P1538 | SOF Support Facility Expansions | MSOR | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | FY 25 | 12000
P1539 | SOF Combat Service Support/Motor Transport Maintenance Expansion | MSOSG | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | ----- | 0
P1540 | SOF EOD Facility | MSOR | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | ----- | 0
P325 | SOF Human Performance Training Center | NSWG2 | Little Creek, VA | NSW | FY 21 | FY 21 | FY 21 | FY 21 | 23200
P600 | SOF Combatant Craft Launch and Recovery Facility | NSWG4 | San Clemente Island, CA | NSW | ----- | FY 23 | ----- | ----- | 0
P502 | SOF Cold Water Training Austere Environment Facility | NSWG3 | Keyport, WA | NSW | ----- | FY 21 | ----- | ----- | 0
P908 | SOF NSWG-4 Operations Support Facility | NSWG4 | Little Creek, VA | NSW | ----- | FY 22 | ----- | ----- | 0
P625 | SOF NSWU-3 Operations Support Facility | NSWG1 | Bahrain | NSW | ----- | FY 22 | ----- | ----- | 0
P906 | SOF Dry Deck Shelter Operations Facility | NSWG3 | Little Creek, VA | NSW | ----- | FY 22 | ----- | ----- | 0
P655 | SOF Land Warfare Training Ranges | NSWCEN | Niland, CA | NSW | ----- | FY 22 | ----- | ----- | 0
P478 | SOF Close Quarters Combat Facility | NSWG3 | Pearl City, HI | NSW | ----- | FY 22 | ----- | ----- | 0
P905 | SOF SEAL Team EIGHTEEN Ops Facility | NSWG11 | Little Creek, VA | NSW | ----- | FY 24 | ----- | ----- | 0
P226 | SOF SRT-2 Operations Facility | NSWG10 | Little Creek, VA | NSW | ----- | FY 23 | ----- | ----- | 0
P304 | SOF Breacher Training Facility | NSWCEN | Fort Pickett, VA | NSW | ----- | FY 23 | ----- | ----- | 0
P556 | SOF Small Craft Operations Facility | NSWCEN | Kodiak, AK | NSW | ----- | FY 23 | ----- | ----- | 0
P624 | SOF NSWU-3 Operations Support Facility #2 | NSWG1 | Bahrain | NSW | ----- | ----- | ----- | ----- | 0
P626 | SOF NSWU-1 Air Operations Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
P627 | SOF NSWU-1 Dive Operations Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
P628 | SOF NSWU-1 Training Support Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
P169 | SOF NAVSCIATTS Training Support Facilities | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P171 | SOF NAVSCIATTS Operations Support Facility | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P172 | SOF NAVSCIATTS Partner Nation Student Quarters | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P175 | SOF Human Performance Training Center | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P178 | SOF SBT-22 Operations Facilities | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P310 | SOF SBT-22 Boat Support Facilities | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P311 | SOF NAVSCIATTS Boat Ramp/Small Craft Berthing | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P629 | SOF NSWU-1 Operations Support Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
P341 | SOCFWD-EA OPERATIONS FACILITY | SOCAFRICA | CAMP LEMONNIER, DJIBOUTI | SOCAF | ----- | ----- | ----- | ----- | 0
87378 | TSOC HQ, SOCAFRICA | SOCAFRICA | KELLEY BARRACKS, STUTTGART, GERMANY | SOCAF | ----- | ----- | ----- | ----- | 0
92602 | TSOC HQ, SOCEUR | SOCEUR | Patch Barracks, Stuttgart, Germany | SOCEUR | ----- | ----- | ----- | ----- | 0
93318 | SOF Training Facility | SOCEUR | Riga, Latvia | SOCEUR | FY 22 | FY 22 | ----- | FY 22 | 14700
93320 | SOF Training Facility | SOCEUR | Kaunas, Lithuania | SOCEUR | FY 23 | FY 22 | ----- | FY 23 | 4600
93317 | SOF Operations Facility | SOCEUR | Riga, Latvia | SOCEUR | FY 24 | FY 22 | ----- | FY 24 | 11350
93319 | SOF Operations Facility | SOCEUR | Kaunas, Lithuania | SOCEUR | FY 25 | FY 22 | ----- | FY 25 | 12600
TBD3 | SOF Operations Facility | SOCEUR | Lubliniec, Poland | SOCEUR | FY 25 | FY 23 | ----- | FY 25 | 13000
SWC1706 | SOF FOB Freedom Upgrades | SWCS | FT BRAGG, NC | USASOC | ----- | FY 22 | ----- | FY 25 | 11000
87442 | SOF Group Headquarters | 1SFG | JOINT BASE LEWIS-MCCHORD, WA | USASOC | ----- | FY 24 | ----- | ----- | 0
SFC1741 | SOF Media Operations Center Modernization and Expansion | 4MISG | FT BRAGG, NC | USASOC | ----- | FY 24 | ----- | ----- | 0
93284 | SOF Hangar | 160SOT | FT CAMPBELL, KY | USASOC | ----- | FY 24 | ----- | ----- | 0
SFC1841 | SOF Research Analytic Center | 4MISG | FT BRAGG, NC | USASOC | ----- | FY 24 | ----- | ----- | 0
93286 | SOF Hangar and Aviation COF | 160SOR | HUNTER AAF, GA | USASOC | ----- | FY 24 | ----- | ----- | 0
91027 | SOF Forward Support Company COFs | 3SFG | FT. BRAGG, NC | USASOC | ----- | FY 24 | ----- | ----- | 0
81910 | SOF Battalion HQ/CO Operations Addition | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 24 | ----- | ----- | 0
93290 | SOF Hangar and Aviation COF | 160SOR | HUNTER AAF, GA | USASOC | ----- | FY 24 | ----- | ----- | 0
93287 | SOF Readiness Facility | 160SOR | HUNTER AAF, GA | USASOC | ----- | FY 24 | ----- | ----- | 0
86023 | SOF SOAT-B HQ | 160SOT | FT CAMPBELL, KY | USASOC | ----- | FY 24 | ----- | ----- | 0
93291 | SOF Regiment HQ Support Annex | 75RGR | FT BENNING, GA | USASOC | ----- | FY 24 | ----- | ----- | 0
SFC1502 | SOF Battalion Tactical Equipment Maintenance Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
81911 | SOF Deployment Readiness Warehouse | 95CABDE | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
87444 | SOF Command Headquarters | SFCMD | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
71230 | SOF Tactical Equipment Maintenance Facility | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
71227 | SOF Admin/Company Operations | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
89190 | SOF Regiment and Battalion HQs | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
69507 | SOF Deployment Equipment Storage Building | 75RGR | FT BENNING, GA | USASOC | ----- | ----- | ----- | ----- | 0
79448 | SOF Human Performance Training Center | 5SFG | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
MIS04 | SOF Expand Battalion Headquarters Building | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
69762 | SOF Deployment Storage Facility (BN Deployment) | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SFC1416 | SOF Company Operations Facility (CRF Co) | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
93289 | SOF Hangar and Aviation Company Operations Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
93288 | SOF Readiness Facility | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1801 | SOF BLDGS 7402 and 7404 Modernization | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SFC1844 | Language Regional Expertise and Cultural Center | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
80779 | SOF D3915 Renovation Bank Hall | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC23 | SOF Battalion Headquarters | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SFC1421 | SOF Language Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC31 | SOF Consolidated COF | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1883 | PSYOP Battalion Operations Facility Renovation (H3014) | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC19 | SOF Battalion Operations Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
87439 | SOF Watercraft Storage Facility | SWCS | NAS KEY WEST, FL | USASOC | ----- | ----- | ----- | ----- | 0
MIS05 | SOF 4th MISG Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC38 | SOF Hangar Addition | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
66820 | SOF Unit Storage / Mobilization Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1886 | 4x HSC Company Operations Facility Renovation (H2908, H2919) | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC21 | SOF TAPO Facility | 160SOR | Joint Base Langley Eustis, VA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1771 | SOF Human Performance Training Center | 7SFG | Eglin AFB, FL | USASOC | ----- | ----- | ----- | ----- | 0
SFC38 | SOF Logistics Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1845 | 1x Three Company Operations Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC35 | SOF Deployment Readiness Warehouse | 160SOR | HUNTER AAF, GA | USASOC | ----- | ----- | ----- | ----- | 0
93285 | SOF Advanced Techniques Facility | SWCS | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
91023 | SOF Advanced Skills Company Facility | 5SFG | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SFC1601 | SOF MISG HQ Renovation | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1409 | SOF Sniper Rappel Tower | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SAC34 | SOF Deployment Readiness Warehouse | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SWC50 | SOF Surgical Strike Training Complex, Phase I | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1881 | Son Tay Utilities and AT/FP Upgrade | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC32 | SOF Deployment Readiness Warehouse | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SWC51 | SOF Surgical Strike Training Complex, Phase II | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
69293 | SOF Maritime Ops Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
91024 | SOF Battalion Operations Facility | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
SAC33 | SOF Deployment Readiness Warehouse | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
81167 | SOF Human Performance Training Center | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC189501 | Cultural Language Facility | 95CABDE | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC36 | SOF Tactical Equipment Maintenance Facility | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SWC47 | SOF Combat Divers Training Support Facility | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
SFC36 | SOF Deployment Readiness Warehouse | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1846 | Operational Skills Detachment | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
ASA1701 | Skills Enhancement and Support Building | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | ----- | ----- | ----- | 0
SFC180101 | SOF Sensitive Activities Training Facility | 1SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1882 | Renovate H2309 (Legal, SHARP, FSRA, EO/EEO) | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
ASA12 | Assessment and Selection Complex Alpha | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
SWC1707 | SOF Tactical Equipment Maintenance Facility | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
ASA1501 | SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | ----- | ----- | ----- | 0
89189 | SOF Tactical Equipment Maintenance Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
81169 | SOF Human Performance Training Facility | 75RGR | HUNTER AAF, GA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1522 | SOF Tactical Equipment Maintenance Facility | SUSB | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
81905 | SOF Consolidated Rigging Facility | 75RGR | HUNTER AAF, GA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1842 | 1x PSYOP Battalion Operations Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
ASA14 | Assessment and Selection Complex Charlie | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
SWC1702 | SOF Surgical Strike Training Complex PH3 | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
81916 | SOF Training and Operations Facility | USASOC | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC62 | SOF Language Facility | 7SFG | Eglin AFB, FL | USASOC | ----- | ----- | ----- | ----- | 0
SFC1843 | 1x PSYOP Battalion Operations Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
ASA13 | Assessment and Selection Complex Bravo | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
36981 | SOF Heavy Drop Rigging Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
81168 | SOF Human Performance Training Center | 75RGR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1701 | SOF Combat Water Survival Training Facility | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SFC1885 | Extend Psyops Lane through Hotel Campus | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SWC30 | SOF Storage Warehouse | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1505 | SOF Combat Water Survival Training Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC06 | SOF Access Control Point | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SWC40 | SOF Combat Diving Training Tank | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
SFC1711 | SOF Combat Water Survival Training Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1884 | Re-establish Son Tay Road and Resurface Sapper Street | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1751 | SOF Combat Water Survival Training Facility | 5SFG | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
81166 | SOF Human Performance Training Center | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SFC1772 | SOF Combat Water Survival Training Facility | 7SFG | Eglin AFB, FL | USASOC | ----- | ----- | ----- | ----- | 0
ASO03 | SOF Parking Deck | USASOC | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SWC1703 | SOF Surgical Strike Training Complex PH4 | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC24 | SOF Hangar | 160SOT | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SWC1704 | SOF Surgical Strike Training Complex, PH 5 | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SWC48 | SOF Consolidated Divers Tng Facilty | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
SWC41 | Renovate KW100 | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
SAC39 | Parking Deck Garage | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SWC31 | SOF Parking Deck Bryant Hall | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SWC1708 | SOF Airborne Staging Facility, MAAF | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC185281 | SOF Rigger Facility Annex | SUSB | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0

## 20190221_MPAT_Solution_v3.2 b
Project Number | Project Title | MIS Program | Location | Capability Sponsor | Must Fund | No Earlier | Stability | Current | Cost
FTEV153011 | SOF Combat Aircraft Parking Apron-North | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 21 | FY 21 | FY 21 | 38310
FTEV103005 | SOF Special Tactics Operations Facility (23 STS) | 24SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 21 | FY 21 | FY 21 | 44810
LXEZ163901 | SOF Human Performance Training Center | 353SOG | KADENA AB, JP | AFSOC | FY 22 | FY 22 | FY 22 | FY 22 | 12960
92242 | SOF Battalion Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 10888
92243 | SOF Operations Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 20543
92351 | SOF Communications Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 4109
92352 | SOF Support Annex | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 22 | FY 22 | FY 21 | FY 22 | 13603
72426 | SOF Military Working Dog Facility | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 21 | FY 21 | FY 21 | 12700
81890 | Training Target Structure | CDA-J1 | CONUS CLASSIFIED | JSOC | ----- | FY 21 | FY 21 | FY 22 | 9200
P1075 | SOF Operations Building Addition | CDA-N | DAM NECK, VA | JSOC | FY 21 | FY 21 | FY 21 | FY 21 | 14400
P1068 | SOF Operations Facility Renovation | CDA-N | DAM NECK, VA | JSOC | FY 21 | FY 21 | FY 21 | FY 21 | 7500
69253 | SOF Close Quarters Combat Range | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 21 | FY 21 | FY 21 | 7200
P1411 | SOF Paraloft Expansion | MSOR | CAMP LEJEUNE, NC | MARSOC | FY 21 | FY 21 | FY 21 | FY 21 | 6228
P907 | SOF Dry Combat Submersible Operations Facility and Command Center | NSWG3 | JOINT EXPEDITIONARY BASE LITTLE CREEK - STORY | NSW | ----- | FY 21 | FY 21 | FY 21 | 54500
P997 | SOF NSWG2 NSWTG Combat Service Support Facilities | NSWG2 | JOINT EXPEDITIONARY BASE LITTLE CREEK - STORY | NSW | FY 21 | FY 21 | FY 21 | FY 21 | 58000
P911 | SOF SERE Training Facility | NSWCEN | Coronado, CA | NSW | ----- | FY 21 | FY 21 | FY 21 | 26500
P951 | SOF ATC Operations Support Facility | NSWCEN | Coronado, CA | NSW | ----- | FY 21 | FY 21 | FY 21 | 20200
P177 | SOF SOUC Training Facility | NSWCEN | Fort Pickett, VA | NSW | ----- | FY 21 | FY 21 | FY 21 | 50000
87437 | SOF Group Headquarters | 3SFG | FT BRAGG, NC | USASOC | FY 21 | FY 21 | FY 21 | FY 21 | 48000
81907 | SOF Consolidated Rigging Facility | 1SFG | JOINT BASE LEWIS-MCCHORD, WA | USASOC | ----- | FY 21 | FY 21 | ----- | 0
66326 | SOF Tactical Equipment Maintenance Facility | 10SFG | FT CARSON, CO | USASOC | ----- | FY 21 | FY 21 | FY 21 | 13600
86022 | SOF Hangar | 160SOR | YUMA, AZ | USASOC | FY 21 | FY 21 | FY 21 | FY 21 | 48732
85959 | SOF Ready Building | SWCS | YUMA, AZ | USASOC | FY 21 | FY 21 | FY 21 | FY 21 | 19051
81906 | SOF Military Free Fall Advanced Training Complex | SWCS | YUMA, AZ | USASOC | ----- | FY 21 | FY 21 | FY 21 | 44800
91018 | SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | FY 21 | FY 21 | FY 21 | 35000
89186 | SOF Tactical Equipment Maintenance Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 21 | FY 21 | FY 21 | 16500
FTEV123008 | SOF Human Performance Training Center | 24SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 21 | FY 22 | FY 22 | 8915
AFSOC180001 | SOF Operations and Maintenance Facilities | SOAWC | DUKE FIELD, FL EGLIN AFB, FL AUX FIELD (DUKE) | AFSOC | FY 22 | FY 22 | FY 22 | FY 22 | 23600
FTEV123003 | SOF Small Arms Range | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 22 | FY 22 | FY 22 | 30400
88658 | SOF Operations Faciltiy | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 22 | FY 22 | FY 22 | 40000
92746 | SOF Operations Facility | CDA-J1 | CONUS CLASSIFIED | JSOC | FY 22 | FY 22 | FY 22 | FY 22 | 100000
90610 | SOF Arms Room Addition | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 22 | FY 22 | FY 22 | 4500
92793 | SOF Operations Building | CDA-F3 | FT BRAGG, NC | JSOC | FY 22 | FY 22 | FY 22 | FY 22 | 12800
P672 | SOF Training Aid and Mock-Up Storage Facility | CDA-N | Dam Neck, VA | JSOC | ----- | FY 22 | FY 22 | FY 22 | 12000
69252 | SOF Baffle Containment for Range 19C | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 22 | FY 22 | FY 22 | 7100
P1284 | SOF Training Tank Expansion | MSOR | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | FY 22 | FY 22 | 12100
P967 | SOF Multi Purpose Canine Facility | NSWG1 | Coronado, CA | NSW | ----- | FY 21 | FY 22 | FY 22 | 7230
P912 | SOF NSWG11 Operations Support Facility | NSWG11 | Coronado, CA | NSW | ----- | FY 22 | FY 22 | FY 22 | 7600
P477 | SOF Indoor Dynamic Shooting Facility | NSWG3 | Pearl City, HI | NSW | ----- | FY 22 | FY 22 | FY 22 | 24845
P870 | SOF UAV Avionics Maintenance and Storage Facility | NSWG10 | Coronado, CA | NSW | ----- | FY 22 | FY 22 | FY 22 | 17400
92792 | SOF MI Battalion Headquarters | 75RGR | FT BENNING, GA | USASOC | FY 22 | FY 22 | FY 22 | FY 22 | 20000
71229 | SOF Tactical Equipment Maintenance Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | FY 22 | FY 22 | FY 22 | 20000
81896 | SOF Indoor Range | 75RGR | HUNTER AAF, GA | USASOC | ----- | FY 22 | FY 22 | FY 22 | 19500
69518 | SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | FY 22 | FY 22 | FY 25 | 35000
69262 | SOF Military Working Dog Facility | 75RGR | HUNTER AAF, GA | USASOC | ----- | FY 22 | FY 22 | FY 22 | 7400
79460 | SOF Group HQs Expansion | 10SFG | FT CARSON, CO | USASOC | ----- | FY 22 | FY 22 | FY 22 | 40000
87447 | SOF Supply Support Activity | 3SFG | FT BRAGG, NC | USASOC | ----- | FY 22 | FY 22 | FY 22 | 6400
92791 | SOF Joint Intelligence Center | SFCMD | FT BRAGG, NC | USASOC | FY 22 | FY 22 | FY 22 | FY 22 | 56100
91019 | SOF USASOC Headquarters Complex | USASOC | FT BRAGG, NC | USASOC | ----- | FY 22 | FY 22 | ----- | 0
FTFA173001 | SOF Fuel Cell Hangar | SOAWC | EGLIN AFB, FL AUX FIELD (DUKE) | AFSOC | ----- | FY 22 | FY 23 | FY 23 | 16200
SHYQ149104 | SOF Simulator Facility EC-130J | 193SOW | HARRISBURG ANG, PA | AFSOC | ----- | FY 22 | FY 23 | FY 23 | 8900
FTEV163002 | SOF Integrated Operations Facility | SOAWC | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | FY 23 | FY 23 | 20500
FTEV073023 | SOF Vehicle Shelter | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 24 | FY 24 | FY 24 | 10400
P155 | SOF Training Facility Addition | CDA-N | Dam Neck, VA | JSOC | ----- | FY 23 | FY 23 | FY 23 | 12300
P619 | SOF Multi-Purpose Range | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | FY 23 | FY 23 | 32000
81893 | SOF Deployment Facility | CDA-A1 | FT Bragg, NC | JSOC | ----- | FY 22 | FY 23 | FY 23 | 9000
P821 | SOF WARCOM Operations Support Facility | NSWCOM | Coronado, CA | NSW | FY 23 | FY 23 | FY 23 | FY 23 | 77000
P901 | SOF TRADET TWO Operations Facility | NSWG2 | Little Creek, VA | NSW | ----- | FY 23 | FY 23 | FY 24 | 25900
KYJM87817 | SOF CONTROLLED HUMIDITY WAREHOUSE | SOCSOUTH | HOMESTEAD, FL | SOCSOUTH | ----- | FY 23 | FY 23 | FY 23 | 9604
KYJM87846 | SOF RIGGING AND DRYING FACILITY | SOCSOUTH | HOMESTEAD, FL | SOCSOUTH | ----- | FY 23 | FY 23 | FY 23 | 3960
80777 | SOF Battalion Operations Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 25 | 41000
87441 | SOF Operations Facility | 5SFG | FT CAMPBELL, KY | USASOC | ----- | FY 23 | FY 23 | FY 23 | 4700
91021 | SOF Deployment Readiness Warehouse | 7SFG | Eglin AFB, FL | USASOC | ----- | FY 23 | FY 23 | FY 23 | 12800
91022 | SOF Technical Support Detachment (TSD) Annex | 3SFG | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 23 | 11800
63848 | SOF Vehicle Maintenance Facility | SWCS | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 23 | 12376
89187 | SOF Multi-Purpose Range Support Facility | SWCS | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 23 | FY 24 | 7500
FTEV173002 | SOF Simulator Facility (Manned ISR) | SOAWC | HURLBURT FIELD, FL | AFSOC | ----- | FY 25 | FY 25 | FY 25 | 8500
CZQZ093010 | SOF Add Alter Simulator Facility (Manned ISR) | SOAWC | CANNON AFB, NM | AFSOC | ----- | ----- | FY 27 | ----- | 0
88654 | SOF SERE Training Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | FY 24 | FY 24 | 13300
P904 | SOF SEAL Team SEVENTEEN Operations Facility | NSWG11 | Coronado, CA | NSW | ----- | FY 22 | FY 24 | FY 24 | 30600
P654 | SOF SBT20 Combatant Craft Operations Facility | NSWG4 | Little Creek, VA | NSW | ----- | FY 22 | FY 24 | FY 24 | 20685
P902 | SOF Combat Swimmer Training Facility | NSWG2 | Key West, FL | NSW | ----- | FY 23 | FY 24 | FY 24 | 12960
P568 | SOF NSWG-4 Finger Piers | NSWG4 | Little Creek, VA | NSW | ----- | FY 23 | FY 24 | FY 24 | 4500
NVZR173711 | SOCCENT Operations Facility | SOCCENT | MacDill AFB, FL | SOCCENT | ----- | FY 24 | FY 24 | FY 24 | 21181
87436 | SOF Battalion Operations Facility | 1SFG | JOINT BASE LEWIS-MCCHORD, WA | USASOC | ----- | FY 23 | FY 24 | FY 25 | 93000
91020 | SOF Language Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 11600
93282 | SOF Hangar | 160SOR | NELLIS AFB, NV | USASOC | ----- | FY 23 | FY 24 | FY 25 | 26000
89192 | SOF MI Battalion Operations Facility | SUSB | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 24 | FY 24 | 21000
93283 | SOF Readiness Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | FY 23 | FY 24 | FY 25 | 17000
81170 | SOF Human Performance Training Center | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 23 | FY 24 | FY 25 | 18500
69279 | SOF Tactical Unmanned Aerial Vehicle Hangar | 1SFG | FT LEWIS, WA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 3800
89193 | SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | FY 23 | FY 24 | FY 25 | 27000
81901 | SOF RSTA Operations Facility | 75RGR | FT BENNING, GA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 4150
86027 | SOF Mackall Company Operations Facilities | SWCS | FT BRAGG, NC | USASOC | ----- | FY 23 | FY 24 | FY 24 | 4350
92790 | SOF Command and Control Facility | SFCMD | FT BRAGG, NC | USASOC | FY 24 | FY 24 | FY 24 | FY 24 | 103000
79445 | SOF Human Performance Training Center | 75RGR | FT BENNING, GA | USASOC | ----- | FY 23 | FY 24 | FY 24 | 10645
FTEV153012 | SOF Parking Apron (AC-130J) | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 22 | ----- | ----- | 0
1055863 | SOF AMU/Hangar (AC-130J) | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | ----- | ----- | 0
CZQZ183001 | SOF Hangar/AMU (CV-22) | 27SOW | CANNON AFB, NM | AFSOC | ----- | FY 23 | ----- | ----- | 0
PXLY073001 | SOF Mission Rehearsal Landing Zone | 27SOW | CANNON AFB, NM | AFSOC | ----- | FY 23 | ----- | FY 25 | 14700
1073614 | SOF Simulator Facility (AC-130J) | SOAWC | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | ----- | ----- | 0
1055876 | SOF Hangar/AMU (MC-130J) | 1SOW | HURLBURT FIELD, FL | AFSOC | ----- | FY 23 | ----- | ----- | 0
PQWY183001 | SOF 22 STS Operational Training Facilities | 24SOW | JOINT BASE LEWIS MCCHORD, WA | AFSOC | ----- | ----- | ----- | ----- | 0
CZQZ073019 | SOF Mobility Aerial Delivery Facility | 27SOW | CANNON AFB, NM | AFSOC | ----- | ----- | ----- | ----- | 0
92241 | SOF Human Performance Training Center | HQSOCOM | BAUMHOLDER, GERMANY | HQSOCOM | FY 23 | FY 23 | FY 23 | FY 23 | 15000
TBD1 | SOF JMWC Facility | HQSOCOM | MacDill AFB, FL | HQSOCOM | ----- | FY 22 | ----- | ----- | 0
88656 | SOF Equipment Development Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
P1052 | SOF Multi-Purpose Ops Facility | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | ----- | ----- | 0
94023 | SOF Operational Ammunition Supply Point | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
92107 | SOF Mission Command Center | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 22 | ----- | ----- | 0
90510 | SOF Deployment and Distribution Center Addition | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
94051 | SOF HPTC Facility | CDA-F3 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | FY 25 | 10000
P167 | SOF Logistics Support Facility | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | ----- | ----- | 0
87741 | SOF Company Operations Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 23 | ----- | ----- | 0
P163 | SOF Tactical Ground Mobility Ops and Storage Facility | CDA-N | DAM NECK, VA | JSOC | ----- | FY 23 | ----- | ----- | 0
TBD2 | Joint Communicaitons Training Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 25 | ----- | ----- | 0
88655 | SOF Training Facility | CDA-J1 | FT BRAGG, NC | JSOC | ----- | FY 25 | ----- | ----- | 0
92397 | SOF Ops Facility | CDA-A1 | FT BRAGG, NC | JSOC | ----- | FY 25 | ----- | ----- | 0
P1537 | SOF Marine Raider Support Battalion and Unmanned Aerial System Facilities | MSOSG | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | FY 25 | 16000
P1538 | SOF Support Facility Expansions | MSOR | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | FY 25 | 12000
P1539 | SOF Combat Service Support/Motor Transport Maintenance Expansion | MSOSG | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | FY 24 | 15000
P1540 | SOF EOD Facility | MSOR | CAMP LEJEUNE, NC | MARSOC | ----- | FY 22 | ----- | FY 25 | 13000
P325 | SOF Human Performance Training Center | NSWG2 | Little Creek, VA | NSW | FY 21 | FY 21 | FY 21 | FY 21 | 23200
P600 | SOF Combatant Craft Launch and Recovery Facility | NSWG4 | San Clemente Island, CA | NSW | ----- | FY 23 | ----- | FY 25 | 14800
P502 | SOF Cold Water Training Austere Environment Facility | NSWG3 | Keyport, WA | NSW | ----- | FY 21 | ----- | ----- | 0
P908 | SOF NSWG-4 Operations Support Facility | NSWG4 | Little Creek, VA | NSW | ----- | FY 22 | ----- | ----- | 0
P625 | SOF NSWU-3 Operations Support Facility | NSWG1 | Bahrain | NSW | ----- | FY 22 | ----- | ----- | 0
P906 | SOF Dry Deck Shelter Operations Facility | NSWG3 | Little Creek, VA | NSW | ----- | FY 22 | ----- | ----- | 0
P655 | SOF Land Warfare Training Ranges | NSWCEN | Niland, CA | NSW | ----- | FY 22 | ----- | ----- | 0
P478 | SOF Close Quarters Combat Facility | NSWG3 | Pearl City, HI | NSW | ----- | FY 22 | ----- | FY 22 | 11600
P905 | SOF SEAL Team EIGHTEEN Ops Facility | NSWG11 | Little Creek, VA | NSW | ----- | FY 24 | ----- | ----- | 0
P226 | SOF SRT-2 Operations Facility | NSWG10 | Little Creek, VA | NSW | ----- | FY 23 | ----- | ----- | 0
P304 | SOF Breacher Training Facility | NSWCEN | Fort Pickett, VA | NSW | ----- | FY 23 | ----- | ----- | 0
P556 | SOF Small Craft Operations Facility | NSWCEN | Kodiak, AK | NSW | ----- | FY 23 | ----- | ----- | 0
P624 | SOF NSWU-3 Operations Support Facility #2 | NSWG1 | Bahrain | NSW | ----- | ----- | ----- | ----- | 0
P626 | SOF NSWU-1 Air Operations Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
P627 | SOF NSWU-1 Dive Operations Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
P628 | SOF NSWU-1 Training Support Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
P169 | SOF NAVSCIATTS Training Support Facilities | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P171 | SOF NAVSCIATTS Operations Support Facility | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P172 | SOF NAVSCIATTS Partner Nation Student Quarters | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P175 | SOF Human Performance Training Center | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P178 | SOF SBT-22 Operations Facilities | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P310 | SOF SBT-22 Boat Support Facilities | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P311 | SOF NAVSCIATTS Boat Ramp/Small Craft Berthing | NSWG4 | Stennis Space Center, MS | NSW | ----- | ----- | ----- | ----- | 0
P629 | SOF NSWU-1 Operations Support Facility | NSWG1 | Guam | NSW | ----- | ----- | ----- | ----- | 0
P341 | SOCFWD-EA OPERATIONS FACILITY | SOCAFRICA | CAMP LEMONNIER, DJIBOUTI | SOCAF | ----- | ----- | ----- | ----- | 0
87378 | TSOC HQ, SOCAFRICA | SOCAFRICA | KELLEY BARRACKS, STUTTGART, GERMANY | SOCAF | ----- | ----- | ----- | ----- | 0
92602 | TSOC HQ, SOCEUR | SOCEUR | Patch Barracks, Stuttgart, Germany | SOCEUR | ----- | ----- | ----- | ----- | 0
93318 | SOF Training Facility | SOCEUR | Riga, Latvia | SOCEUR | FY 22 | FY 22 | ----- | FY 22 | 14700
93320 | SOF Training Facility | SOCEUR | Kaunas, Lithuania | SOCEUR | FY 23 | FY 22 | ----- | FY 23 | 4600
93317 | SOF Operations Facility | SOCEUR | Riga, Latvia | SOCEUR | FY 24 | FY 22 | ----- | FY 24 | 11350
93319 | SOF Operations Facility | SOCEUR | Kaunas, Lithuania | SOCEUR | FY 25 | FY 22 | ----- | FY 25 | 12600
TBD3 | SOF Operations Facility | SOCEUR | Lubliniec, Poland | SOCEUR | FY 25 | FY 23 | ----- | FY 25 | 13000
SWC1706 | SOF FOB Freedom Upgrades | SWCS | FT BRAGG, NC | USASOC | ----- | FY 22 | ----- | FY 25 | 11000
87442 | SOF Group Headquarters | 1SFG | JOINT BASE LEWIS-MCCHORD, WA | USASOC | ----- | FY 24 | ----- | ----- | 0
SFC1741 | SOF Media Operations Center Modernization and Expansion | 4MISG | FT BRAGG, NC | USASOC | ----- | FY 24 | ----- | ----- | 0
93284 | SOF Hangar | 160SOT | FT CAMPBELL, KY | USASOC | ----- | FY 24 | ----- | ----- | 0
SFC1841 | SOF Research Analytic Center | 4MISG | FT BRAGG, NC | USASOC | ----- | FY 24 | ----- | FY 25 | 7500
93286 | SOF Hangar and Aviation COF | 160SOR | HUNTER AAF, GA | USASOC | ----- | FY 24 | ----- | ----- | 0
91027 | SOF Forward Support Company COFs | 3SFG | FT. BRAGG, NC | USASOC | ----- | FY 24 | ----- | ----- | 0
81910 | SOF Battalion HQ/CO Operations Addition | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | FY 24 | ----- | ----- | 0
93290 | SOF Hangar and Aviation COF | 160SOR | HUNTER AAF, GA | USASOC | ----- | FY 24 | ----- | ----- | 0
93287 | SOF Readiness Facility | 160SOR | HUNTER AAF, GA | USASOC | ----- | FY 24 | ----- | FY 25 | 11800
86023 | SOF SOAT-B HQ | 160SOT | FT CAMPBELL, KY | USASOC | ----- | FY 24 | ----- | ----- | 0
93291 | SOF Regiment HQ Support Annex | 75RGR | FT BENNING, GA | USASOC | ----- | FY 24 | ----- | ----- | 0
SFC1502 | SOF Battalion Tactical Equipment Maintenance Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
81911 | SOF Deployment Readiness Warehouse | 95CABDE | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
87444 | SOF Command Headquarters | SFCMD | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
71230 | SOF Tactical Equipment Maintenance Facility | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
71227 | SOF Admin/Company Operations | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
89190 | SOF Regiment and Battalion HQs | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
69507 | SOF Deployment Equipment Storage Building | 75RGR | FT BENNING, GA | USASOC | ----- | ----- | ----- | ----- | 0
79448 | SOF Human Performance Training Center | 5SFG | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
MIS04 | SOF Expand Battalion Headquarters Building | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
69762 | SOF Deployment Storage Facility (BN Deployment) | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SFC1416 | SOF Company Operations Facility (CRF Co) | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
93289 | SOF Hangar and Aviation Company Operations Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
93288 | SOF Readiness Facility | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1801 | SOF BLDGS 7402 and 7404 Modernization | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SFC1844 | Language Regional Expertise and Cultural Center | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
80779 | SOF D3915 Renovation Bank Hall | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC23 | SOF Battalion Headquarters | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SFC1421 | SOF Language Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC31 | SOF Consolidated COF | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1883 | PSYOP Battalion Operations Facility Renovation (H3014) | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC19 | SOF Battalion Operations Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
87439 | SOF Watercraft Storage Facility | SWCS | NAS KEY WEST, FL | USASOC | ----- | ----- | ----- | ----- | 0
MIS05 | SOF 4th MISG Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC38 | SOF Hangar Addition | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
66820 | SOF Unit Storage / Mobilization Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1886 | 4x HSC Company Operations Facility Renovation (H2908, H2919) | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC21 | SOF TAPO Facility | 160SOR | Joint Base Langley Eustis, VA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1771 | SOF Human Performance Training Center | 7SFG | Eglin AFB, FL | USASOC | ----- | ----- | ----- | ----- | 0
SFC38 | SOF Logistics Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1845 | 1x Three Company Operations Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC35 | SOF Deployment Readiness Warehouse | 160SOR | HUNTER AAF, GA | USASOC | ----- | ----- | ----- | ----- | 0
93285 | SOF Advanced Techniques Facility | SWCS | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
91023 | SOF Advanced Skills Company Facility | 5SFG | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SFC1601 | SOF MISG HQ Renovation | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1409 | SOF Sniper Rappel Tower | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SAC34 | SOF Deployment Readiness Warehouse | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SWC50 | SOF Surgical Strike Training Complex, Phase I | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1881 | Son Tay Utilities and AT/FP Upgrade | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC32 | SOF Deployment Readiness Warehouse | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SWC51 | SOF Surgical Strike Training Complex, Phase II | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
69293 | SOF Maritime Ops Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
91024 | SOF Battalion Operations Facility | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
SAC33 | SOF Deployment Readiness Warehouse | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
81167 | SOF Human Performance Training Center | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC189501 | Cultural Language Facility | 95CABDE | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC36 | SOF Tactical Equipment Maintenance Facility | 160SOR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SWC47 | SOF Combat Divers Training Support Facility | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
SFC36 | SOF Deployment Readiness Warehouse | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1846 | Operational Skills Detachment | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
ASA1701 | Skills Enhancement and Support Building | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | ----- | ----- | ----- | 0
SFC180101 | SOF Sensitive Activities Training Facility | 1SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1882 | Renovate H2309 (Legal, SHARP, FSRA, EO/EEO) | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
ASA12 | Assessment and Selection Complex Alpha | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
SWC1707 | SOF Tactical Equipment Maintenance Facility | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
ASA1501 | SOF Battalion Operations Facility | CDA-O | HUMPHRIES ENGINEER CENTER & SUPPORT ACT, VA | USASOC | ----- | ----- | ----- | ----- | 0
89189 | SOF Tactical Equipment Maintenance Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
81169 | SOF Human Performance Training Facility | 75RGR | HUNTER AAF, GA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1522 | SOF Tactical Equipment Maintenance Facility | SUSB | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
81905 | SOF Consolidated Rigging Facility | 75RGR | HUNTER AAF, GA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1842 | 1x PSYOP Battalion Operations Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
ASA14 | Assessment and Selection Complex Charlie | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
SWC1702 | SOF Surgical Strike Training Complex PH3 | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
81916 | SOF Training and Operations Facility | USASOC | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC62 | SOF Language Facility | 7SFG | Eglin AFB, FL | USASOC | ----- | ----- | ----- | ----- | 0
SFC1843 | 1x PSYOP Battalion Operations Facility | 4MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
ASA13 | Assessment and Selection Complex Bravo | CDA-O | WORLDWIDE UNSPECIFIED | USASOC | ----- | ----- | ----- | ----- | 0
36981 | SOF Heavy Drop Rigging Facility | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
81168 | SOF Human Performance Training Center | 75RGR | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1701 | SOF Combat Water Survival Training Facility | 10SFG | FT CARSON, CO | USASOC | ----- | ----- | ----- | ----- | 0
SFC1885 | Extend Psyops Lane through Hotel Campus | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SWC30 | SOF Storage Warehouse | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1505 | SOF Combat Water Survival Training Facility | 3SFG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC06 | SOF Access Control Point | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SWC40 | SOF Combat Diving Training Tank | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
SFC1711 | SOF Combat Water Survival Training Facility | 1SFG | Joint Base Lewis McChord, WA | USASOC | ----- | ----- | ----- | ----- | 0
SFC1884 | Re-establish Son Tay Road and Resurface Sapper Street | 8MISG | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC1751 | SOF Combat Water Survival Training Facility | 5SFG | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
81166 | SOF Human Performance Training Center | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SFC1772 | SOF Combat Water Survival Training Facility | 7SFG | Eglin AFB, FL | USASOC | ----- | ----- | ----- | ----- | 0
ASO03 | SOF Parking Deck | USASOC | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SWC1703 | SOF Surgical Strike Training Complex PH4 | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SAC24 | SOF Hangar | 160SOT | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SWC1704 | SOF Surgical Strike Training Complex, PH 5 | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SWC48 | SOF Consolidated Divers Tng Facilty | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
SWC41 | Renovate KW100 | SWCS | NAS Key West, FL | USASOC | ----- | ----- | ----- | ----- | 0
SAC39 | Parking Deck Garage | 160SOR | FT CAMPBELL, KY | USASOC | ----- | ----- | ----- | ----- | 0
SWC31 | SOF Parking Deck Bryant Hall | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SWC1708 | SOF Airborne Staging Facility, MAAF | SWCS | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0
SFC185281 | SOF Rigger Facility Annex | SUSB | FT BRAGG, NC | USASOC | ----- | ----- | ----- | ----- | 0